## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | CUSTOMER CHURN PREDICTION USING CNN
PROJECT MANAGER | HERISH CHAUDRAY
COMPANY NAME | DAS&CO
DATE | 2023-04-11 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | T | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Collecting Requirements | Roshini | 2023-05-11 | 2023-07-11 | 2 | 100%
1.1.1 | Analysing Requirements | Roshini | 2023-07-11 | 2023-09-11 | 3 | 100%
2 | Data collection | Herish | 2023-10-11 | 17/11/2023 | 7 | 1%
2.1 | Data processing | Nasrool | 17/11/2023 | 20/11/2023 | 4 | 0%
2.1.1 | Feature engineering | Nasrool | 18/11/2023 | 19/11/2023 | 2 | 0%
3 | Building CNN Model | Roshini | 20/11/2023 | 27/11/2023 | 8 | 0%
3.1 | Training the model | Roshini | 27/11/2023 | 30/11/2023 | 4 | 0%
3.2 | Evaluating metrics | Farhan | 30/11/2023 | 2023-03-12 | 4
3.3 | Reconstructing model structure | Farhan | 2023-04-12 | 2023-07-12 | 4 | 0%
4 | Testing model | Nasrool | 2023-08-12 | 2023-10-12 | 5 | 0%
4.1 | Evaluting training metrics | Nasrool | 2023-12-12 | 13/12/2023 | 2 | 0%
5 | Testing system | Herish | 15/12/2023 | 21/12/2023 | 7 | 0%